PRS

SALVAGE VEHICLE AUCTION PLATFORM

4-Phase Delivery Plan

& Payment Schedule

CLIENT DELIVERY & PAYMENT AGREEMENT

| Project | PRS — Salvage Vehicle Auction Platform |
| --- | --- |
| Document Type | 4-Phase Delivery Plan & Payment Schedule |
| Agreed Budget | PKR 150,000 (Fixed) |
| Delivery Model | Phase-gated · Client approval · Payment before next phase |
| Estimated Timeline | ~25 calendar days (excluding approval wait time) |
| Document Date | July 2026 |
| Status | Confidential — For Client Review |

Aligned to the PRS System Concept Document (July 2026) — Year-1 Pakistan MVP

1. How This Engagement Works

The project is delivered in four phases. After each phase, the client reviews the deliverables, approves in writing, and pays the phase invoice. The next phase starts only after payment is received.

Step 1: Developer completes the phase deliverables on a staging / demo environment.

Step 2: Client reviews against the phase Approval Checklist (up to 3 business days).

Step 3: Client sends written approval (email or WhatsApp is acceptable).

Step 4: Client pays the phase amount as per the schedule below.

Step 5: Next phase begins only after payment clears.

Important: Days spent waiting for client review or payment do not count against the delivery timeline. Unapproved or unpaid phases pause the schedule.

2. Payment Summary — PKR 150,000

| Phase | Name | Payment (PKR) | % | Approx. Days |
| --- | --- | --- | --- | --- |
| 1 | Foundation & Access | 40,000 | 27% | Days 1–6 |
| 2 | Listings & Folders | 40,000 | 27% | Days 7–13 |
| 3 | Auctions, Bids & Controls | 40,000 | 27% | Days 14–20 |
| 4 | Notifications, Polish & Go-Live | 30,000 | 20% | Days 21–25 |
| Total | Full MVP Delivery | 150,000 | 100% | ~25 days |

Payment method: Bank transfer (details provided on each phase invoice). Invoice is issued when the phase is ready for review and due upon approval (or within 2 business days of approval).

3. Items to Confirm Before Kickoff

Please confirm the following before Phase 1 begins. If no reply within 3 days of kickoff, the defaults below will be used.

| Item | Default if Not Confirmed |
| --- | --- |
| Auction length | Seller sets end date/time when publishing |
| Platform fee % (seller) | 2% of final sale (admin-configurable later) |
| Platform fee % (buyer) | 2% of final sale (admin-configurable later) |
| Non-payment fine (unblock) | PKR 5,000 flat — admin confirms bank receipt |
| Payment window after win | 7 days (seller can extend) |
| Brand assets | Text “PRS” + green/white theme until logo provided |

Not Included in PKR 150,000

JazzCash / card payment gateways · Native Android/iOS apps · AI valuation · Blockchain · Multi-country localization · Advanced analytics dashboards · Live WebSocket bidding · Company “follow” alerts. These can be quoted separately as Phase 5+.

4. Phase 1 — Foundation & Access

| Payment on Approval | Duration | Starts When |
| --- | --- | --- |
| PKR 40,000 | ~6 days | Project kickoff |

Goal

Public face of PRS, secure registration/login for all roles, and admin ability to approve users.

Deliverables

Landing page (green & white): platform intro, Sign Up / Login, role selection

Registration — Insurance Company (name, phone, email, NTN/tax, location, password, policy accept)

Registration — Salvage Dealer (name/company, tax/ID, phone optional, email, password, policy accept)

Registration — Private Seller (personal details, contact, email, password, policy accept)

Login / logout / secure sessions

User status workflow: Pending → Approved / Suspended

Admin panel (basic): list users, approve, suspend

Responsive layout shell (mobile + desktop)

Staging URL for client review

Demo Walkthrough

Open landing → sign up as each of the three roles

Admin logs in → approves each user

Approved users can log in; pending users cannot use the app

Client Approval Checklist

☐  Landing looks professional enough to proceed

☐  All three registration forms work

☐  Policy acceptance is required at signup

☐  Admin can approve and suspend users

☐  Site is usable on a mobile browser

Not in Phase 1

Vehicle upload, folders, bidding, notifications, fees, or blocking.

5. Phase 2 — Listings & Company Folders

| Payment on Approval | Duration | Starts When |
| --- | --- | --- |
| PKR 40,000 | ~7 days | Phase 1 approved + PKR 40,000 paid |

Goal

Insurance companies and private sellers manage vehicles; dealers browse inventory by company folder.

Deliverables

Insurance dashboard with company folder for their listings

Add/edit vehicle: multiple photos, make, model, variant (optional), registration no., company value (optional), comments

Draft vs Publish workflow (save drafts for later batch auctions)

Private seller dashboard: list and manage own vehicles

Dealer dashboard: side menu of insurance company folders

Open folder → view that company’s live vehicles; vehicle detail page (view only)

Image upload to cloud/storage

Admin: basic listing moderation (view / hide)

Demo Walkthrough

Insurance user uploads 2–3 vehicles (draft + publish)

Dealer opens that company’s folder and sees published vehicles only

Private seller lists one vehicle

Mobile: browse folder and open a vehicle

Client Approval Checklist

☐  Photos and required fields work correctly

☐  Drafts are hidden from dealers; published listings appear

☐  Folders show the correct company’s vehicles

☐  Private seller can list a vehicle

☐  Layout remains clean on mobile

Not in Phase 2

Placing bids, auction end logic, winner selection, blocking, fees, or email alerts.

6. Phase 3 — Auctions, Bids & Business Controls

| Payment on Approval | Duration | Starts When |
| --- | --- | --- |
| PKR 40,000 | ~7 days | Phase 2 approved + PKR 40,000 paid |

Goal

Complete marketplace loop: bid → win → offline payment tracking → block/fine → platform fee ledger.

Deliverables

Dealer bidding on live insurance auctions

Asymmetric visibility: dealers see highest bid amount only; sellers see full bidder names + amounts

Auction close: seller sets end date/time; highest bid wins

In-app status updates for winner and seller

Private seller flow: offers with Accept / Reject (not automatic highest-wins)

Payment window: default 7 days; seller can extend; statuses awaiting / paid / overdue

Vehicle payment remains offline between buyer and seller (outside the platform)

Blocking: insurance can block non-paying winners from future auctions with that company

Unblock after fine: admin confirms bank transfer receipt (no online gateway in this budget)

Platform fee ledger for seller + winning buyer; mark paid manually

Admin: monitor bids, blocks, fee statuses, basic dispute actions

Demo Walkthrough

Two dealers bid; insurance sees both names; dealers do not see each other

Auction ends → highest bidder wins

Mark overdue → block dealer → dealer cannot bid on that company

Admin confirms fine → dealer unblocked

Private seller accepts one offer

Fee ledger shows both-side fees

Client Approval Checklist

☐  Asymmetric bid visibility works as described

☐  Highest bid wins on insurance auctions

☐  Private accept/reject works

☐  Block / unblock with admin-confirmed fine works

☐  7-day window and extend work

☐  Fee ledger is clear for admin use

Not in Phase 3

Polished email templates, final-domain go-live, final visual polish, or training documentation.

7. Phase 4 — Notifications, Polish & Go-Live

| Payment on Approval | Duration | Starts When |
| --- | --- | --- |
| PKR 30,000 | ~5 days | Phase 3 approved + PKR 40,000 paid |

Goal

Production-ready release: email notifications, polish, live deploy, and final client UAT sign-off.

Deliverables

Email notifications: outbid, win (with seller contact basics), new bid/offer, auction ended

Optional simple admin announcement email capability

UI polish pass (theme consistency, navigation, mobile fixes)

Bug fixes from Phases 1–3 within agreed scope

Production deploy on client domain (if provided) or agreed host

Short admin/ops handoff notes (approve users, confirm fees/fines)

Final UAT session with client

Demo Walkthrough

Full flow on production URL: register → approve → list → bid → win

Show sample notification emails

Admin day-to-day walkthrough

Client Approval Checklist

☐  Production site reachable on agreed URL

☐  Core emails received during testing

☐  No blocking bugs on main journeys

☐  Client accepts MVP as complete for the PKR 150,000 scope

After Phase 4 payment, the MVP project is closed. Further features require a new quote (Phase 5+).

8. Change Requests & Revisions

| Type | Policy |
| --- | --- |
| Bugs (does not work as in this plan) | Fixed free during the active phase and in Phase 4 polish |
| Small text / logo / color tweaks | Included if requested during the same phase review |
| New features not listed above | Separate quote / paid Phase 5 |
| Scope change mid-phase | Timeline pauses; written change order + fee if effort grows |

Up to two (2) review rounds per phase during the 3-day approval window. Extra redesign rounds may shift the timeline or require a small add-on fee, agreed in writing.

9. Responsibilities

Client

Provide logo, brand colors (if different), contact info, fee %, and fine amount

Approve and pay each phase on time

Nominate one decision-maker for approvals

Participate in Phase 4 UAT with sample data if possible

Arrange domain DNS if using the client’s domain

Developer

Deliver each phase as listed in this document

Keep a staging environment available for review

Protect bid privacy (dealers never see other bidders via the interface or API)

Hand over production access and short ops notes at Phase 4

Keep the total fixed at PKR 150,000 for the scope in this document

10. Quick Reference — Approval & Pay Cycle

| After Approving | Pay (PKR) | Then Starts |
| --- | --- | --- |
| Phase 1 | 40,000 | Phase 2 |
| Phase 2 | 40,000 | Phase 3 |
| Phase 3 | 40,000 | Phase 4 |
| Phase 4 | 30,000 | Project closed (MVP) |
| Grand Total | 150,000 | — |

11. Sign-Off

By signing below (or confirming by email/WhatsApp with this document attached), both parties agree to the phase scope, timeline rules, and payment schedule.

| Client | Developer |
| --- | --- |
| Name: | Name: |
| Signature / Confirmation: | Signature / Confirmation: |
| Date: | Date: |
| Contact: | Contact: |

— End of Document —

PRS Platform · 4-Phase Delivery Plan · Confidential

Aligned to System Concept Document (July 2026) — Year-1 Pakistan MVP only